## ICE-PIGGAREP
ITEMIZED COST ESTIMATES BY ACTIVITY (ICL) | [7 empty] | For Qtr: | 4 | Year | 2012
Country:
Currency | USD
Activity No. (refer AWP or QWP) REF: | ACTIVITY ITEMS | PLANNED AMOUNT (USD $) | CHILD CODE | (refer to COA) | ACTUAL (ACQUITTED) | OUTCOME | DIRECT | FOR UNDP USE ONLY - ATLAS ALLOCATION
|  |  | PLANNED | ACTUAL | AMOUNT | COMPONENT | PAYMENT | Project ID | Activity ID | Account | Fund Donor
|  | (Fill IN at beginning of quarter) | (Fill IN at beginning of quarter) | (Fill in at END of quarter) | (Fill in at END of quarter) | (Fill IN at beginning of quarter)
Note on F6: peniaminal: At the end of the quarter - there may be changes in the child code allocation of the said amount. The new code must be inserted here therefore. This does not / should not always happen if good allocation of child codes were made at the beginning of the quarter (column D in this example).

## QWP 2013
2013 ANNUAL WORK PLAN | [12 empty] | 2014 ANNUAL WORK PLAN
Country | Act No. | Outcome | Fund | Account | Activities | Lead/collaborating Agencies | Q12013 | Q22013 | Q32013 | Q42013 | total 2013 | REMARKS | Q12014 | Q22014 | Q32014 | Q42014 | total 2014 | APPROVED $total per country
CK | CI-13-01 | Technical | GEF | 71200 | Rakahanga Wind/Solar Hybrid FS Project | PM office/SPREP |  |  |  |  | 0 | supervision/monitoring component left | 20800 |  |  |  | 20800 | 20800
| CI-13-02 | Technical | GEF | 71200 | Pukapuka/Nassau Solar Grid Connect Project | PM office/SPREP |  |  |  |  | 0 | supervision/monitoring component left | 25500 |  |  |  | 25500 | 25500
| CI-13-04 | Technical | GEF | 71200 | Manihiki Solar PV Mini-grid connected project | PM office/SPREP |  |  |  |  | 0 | supervision/monitoring component left | 25500 |  |  |  | 25500 | 25500
| CI-13-03 | Technical | GEF | 71200 | Atiu Biomass Project Feasibility study | PM office/SPREP |  | 14700 |  |  | 14700 | completed |  |  |  |  | 0 | 14700
| CI-13-05 | Technical | GEF | 71200 | Preparatory work ffor the designing of renewable energy projects in the outer islands of the Cook islands (north). | PM office/SPREP |  |  |  | 111148.4 | 111148.4 | new activity for 2013 but same consultancy engaged to include north islands | 6788.6 |  |  |  | 6788.6 | 117937
total for CK | [7 empty] | 14700 | 0 | 111148.4 | 125848.4 |  | 78588.6 | 0 | 0 | 0 | 78588.6
FJ | FJ-13-03 | POLICY | GEF | 71200 | Formulation of Net-Metering Policy for Grid - Connected Renewable Energy Generation Systems in Fiji | DOE/SPREP |  |  |  |  | 0 | outstanding activity from 2011 | 30000 |  |  |  | 30000 | 30000
| total for FJ | [6 empty] | 0 | 0 | 0 | 0 |  | 30000 | 0 | 0 | 0 | 30000
KI | [16 empty] | 0 | 0
total for KI | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
NR | NR-13-01 | Technical | GEF | 75700 | local solar PV training | Nauru Utility/SPREP |  |  |  | 7100 | 7100 | contract signed and activity conducted 17-20 Dec 2013 | 7900 |  |  |  | 7900 | 15000
total for NR | [7 empty] | 0 | 0 | 7100 | 7100 |  | 7900 | 0 | 0 | 0 | 7900
NU | NU-13-01 | Technical / Awareness | GEF | 71200/75700 | Increasing the Impact of Grid-Connected Solar PV Generation | NPC/SPREP |  |  |  | 23763 | 23763 | ongoing from 2010 to be completed in Q4, 2013 | 0 |  |  |  | 0 | 23763
[17 empty] | 0 | 0
total for NU | [7 empty] | 0 | 0 | 23763 | 23763 |  | 0 | 0 | 0 | 0 | 0
PG | [17 empty] | 0
total for PG | [7 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
WS | SA-13-01 | Technical | GEF | 71600 | RE site visit (fact finding) | MOF/MNRE/EPC/SPREP |  |  | 17525.12 |  | 17525.12 | completed in quarter 3 |  |  |  |  | 0 | 17525.12
| SA-13-02 | Awareness | GEF | 75700 | RE awareness day for Upolu and Savaii | MOF/MNRE/EPC/SPREP |  | 20084.4 | 17915.6 |  | 38000 | completed in quarter 2 and 3 |  |  |  |  | 0 | 38000
| SA-13-03 | technical | GEF | 72500 | Consumerables for Samoa RE Resource assessments | SROS/MOF/SPREP |  |  |  | 20000 | 20000 | completed in quarter 4 |  |  |  |  | 0 | 20000
total for SA | [7 empty] | 20084.4 | 35440.72 | 20000 | 75525.12 |  | 0 | 0 | 0 | 0 | 0
SB | SI-13-01 | Technical | GEF | 71200 | Solomon Islands Wind Monitoring and Resource Assessment Project | Energy Division/SPREP |  |  |  | 9073 | 9073 | ongoing activity from 2012 to be completed by Q1, 2014 | 27220 |  |  | 9073 | 36293 | 45366
|  | awareness | GEF | 75700 | Tina Hydro Development Awareness | Energy Division/SPREP |  |  |  | 35400 | 35400 | new activity for 2013 |  |  |  |  | 0 | 35400
total for SI | [7 empty] | 0 | 0 | 44473 | 44473 |  | 27220 | 0 | 0 | 9073 | 36293
TO | TO-13-01 | Technical | GEF | 71200/75700 | Capacity Strengthening to Sustain and Disseminate Renewable Energy Knowledge | Energy Office/SPREP |  |  |  | 8795 | 8795 | contract to be signed in quarter 4, 2013 | 100893 |  |  |  | 100893 | 109688
total for TO | [7 empty] | 0 | 0 | 8795 | 8795 |  | 100893 | 0 | 0 | 0 | 100893
TV | TU-13-01 | Technical | GEF | 71200 | Improving reliable access to modern energy services through solar PV systems for rural areas (outer islands) of Tuvalu | TEC/SPREP |  |  |  | 22000 | 22000 | training component commenced implementation in quarter 3 and 4 | 49300 | 156700 | 35570 |  | 241570 | 263570
|  | Technical | GEF | 71200 | The Study of Electricity Tariff Reform including development of Net-metering Policy | TEC/SPREP |  |  |  | 25400 | 25400 | contract signed and first invoice received 40% of contract value | 50600 |  |  |  | 50600 | 76000
total for TU | [7 empty] | 0 | 0 | 47400 | 47400 |  | 99900 | 156700 | 35570 | 0 | 292170
VU | VU-13-01 | Technical | GEF | 71200 | Vanuatu Wind Monitoring Project | Energy Uni/SPREP |  |  | 14925 |  | 14925 | completed in quarter 3, 2013 |  |  |  |  | 0 | 14925
| VU-13-02 | Technical | GEF | 71200 | Developing Productive Use of Renewable Energy - Social aspects of Vanuatu Talise hydro Project | Energy Uni/SPREP |  |  |  |  | 0 | deferred to quarter 1, 2014 | 14982 |  |  |  | 14982 | 14982
| VU-13-03 | Technical | GEF | 71600 | Technical Site Visit and Capacity Building Workshop As Part of the Talise Hydropower Project | Energy Uni/SPREP |  | 15000 |  |  | 15000 | completed |  |  |  |  | 0 | 15000
| VU-13-04 | Technical | GEF | 71200 | Development of a wind atlas for Vanuatu | Energy Uni/SPREP |  |  |  |  | 0 | deferred to quarter 1, 2014 with preparatory paper work to be completed by end of quarter 4, 2013 | 50000 |  |  |  | 50000 | 50000
total for VU | [7 empty] | 15000 | 14925 | 0 | 29925 |  | 64982 | 0 | 0 | 0 | 64982
TOTAL PIGGAREP | [6 empty] | 0 | 49784.4 | 50365.72 | 262679.4 | 362829.52 |  | 409483.6 | 156700 | 35570 | 9073 | 610826.6
PIGGAREP PLUS | [17 empty] | total per country
FSM | FSM-13-01 | Technical | SIDS DOCK | 71200 | Sustaining RE and EE measures in Micronesia (SREEM)-FSM | Energy Office/SPREP |  |  |  | 155440 | 155440 | PIGGAREP+ | 60000 | 162000 | 100000 | 25000 | 347000 | 502440 | FSM
PALAU | PAL-13-01 | Technical | SIDS DOCK | 71200 | Sustaining RE and EE measures in Micronesia (SREEM)-PALAU | Energy Office/SPREP |  |  |  | 18000 | 18000 | PIGGAREP+ | 116900 | 29400 | 6200 | 28000 | 180500 | 198500 | Palau
RMI | RMI-13-01 | Technical | SIDS DOCK | 71200 | Sustaining RE and EE measures in Micronesia (SREEM)-RMI | Energy Office/SPREP |  |  |  | 98500 | 98500 | PIGGAREP+ | 27000 | 77000 | 27000 | 25000 | 156000 | 254500 | RMI
SB | SB-13-01 | Technical | SIDS DOCK | 71200 | Solar PV powered Rural Telecommunication system | Energy Office/SPREP |  |  |  | 24000 | 24000 | PIGGAREP+ | 183500 | 85000 | 22000 | 31000 | 321500 | 345500 | SB
TO | TO-13-01 | Technical | SIDS DOCK | 71200 | Solar PV powered Well Water pumping systems in Haapai Islands | TERM/Energy Office/SPREP |  |  |  | 38000 | 38000 | PIGGAREP+ | 207000 | 118000 | 17000 | 30000 | 372000 | 410000 | TO
TU | TU-13-01 | Technical | SIDS DOCK | 71200 | Energy Efficiency Demonstration House | TEC/SPREP |  |  |  | 16000 | 16000 | PIGGAREP+ | 163400 | 36000 | 8800 | 25000 | 233200 | 249200 | TV
TOTAL FOR PIGGAREP PLUS |  |  | SIDS DOCK |  |  |  | 0 | 0 | 0 | 349940 | 349940 |  | 757800 | 507400 | 181000 | 164000 | 1610200 | 1960140 | total
TOTAL FOR NATIONAL ACTIVITIES | [7 empty] | 49784.4 | 50365.72 | 612619.4 | 712769.52 |  | 1167283.6 | 664100 | 216570 | 173073 | 2221026.6 | 2933796.12
0
REGIONAL ACTIVITIES | [17 empty] | 0
1 | RE-12-01 | Policy | GEF | 71200 /71600 /75700 | Multipartite Review Meeting and CBA trainings | SPREP |  |  | 55000 |  | 55000 | Closing MPR for current PIGGAREP and 1st MPR for PIGGAREP+ in 2014 |  |  | 75000 |  | 75000
|  | Market | GEF | 71200 | Palau Devt bank followup | IUCN/SPREP |  | 8328 |  |  | 8328 | completed in quarter 2, 2013 |  |  |  |  | 0
|  | institutional Strengthening | GEF | 71200 | IRENA-PIREP update | IRENA/SPREP |  | 23372.5 | 3627.5 |  | 27000 | completed in quarter 3, 2013 |  |  |  |  | 0
|  | institutional Strengthening | GEF | 71200 | support for the development of a RESCO Manager 3, Help file and user manual |  |  | 16000 |  |  | 16000 | completed in quarter 2.2013 |  |  |  |  | 0
|  | institutional Strengthening | GEF | 71200 | REGIONAL TRAINING (RESCO Manager including Help file and user manual training workshop and gender indicators |  |  | 20000 | 19517 |  | 39517 | completed in quarter 3, 2013 |  |  |  |  | 0
|  | Technical | GEF | 75700 | Online training of GHG | [5 empty] | 0 | new proposed activity during MPR 2013 | 10000 |  |  |  | 10000
TOTAL FOR REGIONAL ACTIVITIES | [7 empty] | 67700.5 | 78144.5 | 0 | 145845 |  | 10000 | 0 | 75000 | 0 | 85000
PMO COSTS
| PM-13-01 |  | GEF | 71200 | International Consultants (PM/CCMO) |  | 37468.85 | 40000 | 65601.42 | 50000 | 193070.27 |  | 45000 | 45000 | 45000 | 45000 | 180000
| PM-13-02 |  | GEF | 71300 | Local Consultant - APA |  |  | 3500 | 2465.52 | 0 | 5965.52 |  | 1000 | 2000 | 1000 | 1000 | 5000
| PM-13-03 |  | GEF | 73510 | Administration Fees |  |  | 4500 | 11064.45 | 6750 | 22314.45 |  | 6750 | 4500 | 4500 | 4500 | 20250
| PM-13-04 |  | GEF | 71400 | Contractual Services - Ind |  |  | 1000 | 0 | 0 | 1000 |  | 1000 | 1000 | 1000 | 1000 | 4000
| PM-13-05 |  | GEF | 71600 | Travel, Audits and Reviews |  | 22043.95 | 25304 | 20456.06 | 5000 | 72804.01 |  | 10000 | 10000 | 20000 | 20000 | 60000
| PM-13-06 |  | GEF | 72100 | Contractual Services - Co |  |  | 2000 | 0 | 0 | 2000 |  | 0 | 1000 | 1000 | 1000 | 3000
| PM-13-07 |  | GEF | 72200 | Equip and Furniture |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| PM-13-08 |  | GEF | 72400 | Comm & Audio Equip |  | 1187.94 | 900 | 35.46 | 200 | 2323.4 |  | 100 | 100 | 100 | 0 | 300
| PM-13-09 |  | GEF | 74200 | Audio Visual and Print Prod |  |  | 6043 | 506.02 | 500 | 7049.02 |  | 2000 | 100 | 100 | 100 | 2300
| PM-13-10 |  | GEF | 72500 | Supplies |  | 186.28 | 300 |  | 100 | 586.28 |  | 100 | 100 | 100 | 0 | 300
| PM-13-11 |  | GEF | 72800 | Info Tech Equip |  |  | 500 | 712.91 | 150 | 1362.91 |  | 200 | 100 | 100 | 0 | 400
| PM-13-12 |  | GEF | 75700 | Workshop Training/Learning costs |  |  | 500 | 0 | 0 | 500 |  | 200 | 200 | 200 | 0 | 600
| PM-13-13 |  | GEF | 74500 | Miscellaneous |  |  | 60 | 25.43 | 50 | 135.43 |  | 100 | 100 | 100 | 102.24 | 402.24
TOTAL FOR PMO | [6 empty] | 60887.02 | 84607 | 100867.27 | 62750 | 309111.29 |  | 66450 | 64200 | 73200 | 72702.24 | 276552.24
GRAND TOTAL | [6 empty] | 60887.02 | 202091.9 | 229377.49 | 675369.4 | 1167725.81 |  | 1243733.6 | 728300 | 364770 | 245775.24 | 2582578.84
summary
PIGGAREP PROJECT |  | OUR REF | AP 3/11/1 |  |  | Prepared & Reviewed by: | Sili'a Kilepoa Ualesi |  | Date:
PROJECT CODE: | 52573 | [5 empty] | PIGGAREP - Project Manager
AWARD ID: | 44633
AWARD TITLE: | PIMS 3462 CC FSP: PIGGAREP
SUMMARY OF PROPOSED BUDGET AWP 2013 | [5 empty] | P. Assurance: | Alofa Tuuau |  | Date:
Finance & Administration Adviser
DONOR | GEF |  | TOTAL
COUNTRIES | 712769.52 |  | 712769.52
REGIONAL | 145845 |  | 145845
PMO | 309111.29 |  | 309111.29 |  |  | Endorsed by: | David Sheppard |  | Date:
| 1167725.81 |  | 1167725.81 |  |  |  | Director General - SPREP
[6 empty] | Submitted On: | 17th April 2013