## Original
Project Design Matrix (PDM) - Fiji |  |  |  |  | PDM: Version 0
Project Title: Japanese Technical Cooperation Project for Promotion of Regional Initiative on Solid Waste Management in Pacific Island Countries (J-PRISM)
Target Group：C/Ps of DOE |  |  | Final Beneficiaries: Citizens of Fiji |  | Project period:5 years
Implementing Agency: DOE, LCC, NTC |  |  | Target Area: The Republic of the Fiji Islands
Narrative Summary |  |  | Objectively Verifiable Indicators | Means of Verifications | Important Assumptions
Overall Goal
Sustainable management of solid waste in the Pacific Region is enhanced. |  |  | 1.To be discussed | To be advised
Project Purpose |  |  |  |  | 1. Natural disaster would not drastically affect the collaboration among PICs and SPREP. 2. Political changes of PICs would not drastically affect the collaboration among PICs and SPREP.
Human and institutional capacity base for sustainable Solid Waste Management in the Pacific Region is strengthened through implementation of the Pacific Regional Solid Waste Management Strategy (2010-2015) (RS2010) |  |  | 1. # of experts (Trainers) in the field of 3R listed in the SPREP inventory | SPREP (Regional inventory of skilled people)
|  |  | 2. Regional training program organized by Fiji is established. | Regional training program
# | Priorities under RS2010 | Outputs
1 | Sustainable Financing |  |  |  | 1. Political change in Fiji will not drastically affect the project implementation.
2-1 | 3Rs/4Rs | Output 1: Follow-up of implementation of national 3R strategy | 1-1 Percentage of population whose local authorities have been implementing the 3R promotion as opposed to the whole population of the Western Division. 1-2 The same indicator for other Divisions | 1-1 3R annual monitoring reports from councils and rural authorities 1-2 Same as above
2-2 | Waste Disposal
2-3 | Waste Collection
3 | Legislation
4 | Awareness/Communication/Education
5 | Capacity Building | Output 2: Training program on 3R is developed. | 2-1 Training manuals/materials 2-2 # of trainig conducted and # of participants | 2-1 Developed manuals/materials 2-2 Participants lists
6 | Environmental Monitoring
7 | Policy,Planning, Performance
8 | Solid Waste Industry
* | Monitoring system of RS2010
| Activities |  | Inputs
|  | Please see PO for details. | Japanese Side | Fiji side | 1.Counterpart personnel keep working in the field of SWM. 2. Disasters, such as severe rain storm will not drastically affect the progress of project activities. 3. Necessary budget to carry out activities is allocated by the government.
|  |  | Dispatch of JICA experts | Assignment of National PD/PM and CPs
|  |  | Provision of equipment and materials Provision of Regional, sub-regional and in-country workshops / training | Local Costs Sharing Provision of necessary land/facility, work space
|  |  | Loca cost support |  | Pre-condition

## 18Feb12_rev.1
Project Design Matrix (PDM) - Fiji |  |  |  |  | PDM: Version 1
Project Title: Japanese Technical Cooperation Project for Promotion of Regional Initiative on Solid Waste Management in Pacific Island Countries (J-PRISM)
Target Group：C/Ps of DOE, LCC, NTC and other Municipalities |  |  | Final Beneficiaries: Citizens of Fiji |  | Project period:5 years
Implementing Agency: DOE, DoLG, LCC, NTC and other Municipalities |  |  | Target Area: The Republic of the Fiji Islands |  | Date issued: 28th Feb., 2012
Narrative Summary |  |  | Objectively Verifiable Indicators | Means of Verifications | Important Assumptions
Overall Goal
Sustainable management of solid waste in the Pacific Region is enhanced. |  |  | 1.To be discussed | To be advised
Project Purpose |  |  |  |  | 1. Natural disaster would not drastically affect the collaboration among PICs and SPREP. 2. Political changes of PICs would not drastically affect the collaboration among PICs and SPREP.
Human and institutional capacity base for sustainable Solid Waste Management in the Pacific Region is strengthened through implementation of the Pacific Regional Solid Waste Management Strategy (2010-2015) (RS2010) |  |  | 1. # of experts (Trainers) in the field of 3R listed in the SPREP inventory | SPREP (Regional inventory of skilled people)
|  |  | 2. Regional training program organized by Fiji is established. | Regional training program
# | Priorities under RS2010 | Outputs
1 | Sustainable Financing |  |  |  | 1. Political change in Fiji will not drastically affect the project implementation.
2-1 | 3Rs/4Rs | Output 1: Follow-up of implementation of national 3R strategy1) | 1-1 Percentage of population whose local authorities have been implementing the 3R promotion as opposed to the whole population of the Western Division. 1-2 The same indicator for other Divisions | 1-1 3R annual monitoring reports from councils and rural authorities 1-2 Same as above
2-2 | Waste Disposal
2-3 | Waste Collection
3 | Legislation
4 | Awareness/Communication/Education
5 | Capacity Building | Output 2: Training program on 3R is developed. | 2-1 Training manuals/materials 2-2 # of trainig conducted and # of participants | 2-1 Developed manuals/materials 2-2 Participants lists
6 | Environmental Monitoring
7 | Policy,Planning, Performance
8 | Solid Waste Industry
* | Monitoring system of RS2010
| Activities |  | Inputs
|  | Please see PO for details. | Japanese Side | Fiji side | 1.Counterpart personnel keep working in the field of SWM. 2. Disasters, such as severe rain storm will not drastically affect the progress of project activities. 3. Necessary budget to carry out activities is allocated by the government.
|  |  | Dispatch of JICA experts | Assignment of National PD/PM and CPs
|  |  | Provision of equipment and materials Provision of Regional, sub-regional and in-country workshops / training | Local Costs Sharing Provision of necessary land/facility, work space
|  |  | Loca cost support |  | Pre-condition
1): National 3R strategy is regarded as National 3R policy and National SWM strategy (2011 -1014)

## 03Mar14_rev.2
Project Design Matrix (PDM) - Fiji |  |  |  |  | PDM: Version 2
Project Title: Japanese Technical Cooperation Project for Promotion of Regional Initiative on Solid Waste Management in Pacific Island Countries (J-PRISM)
Target Group：C/Ps of DOE, LCC, NTC, STC, BTC, TTC, RTC, SCC |  |  | Final Beneficiaries: Citizens of Fiji |  | Project period:5 years
Implementing Agency: DOE, DoLG, LCC, NTC, STC, BTC, TTC, RTC, SCC |  |  | Target Area: The Republic of the Fiji Islands |  | Date issued: 3rd Mar., 2014
Narrative Summary |  |  | Objectively Verifiable Indicators | Means of Verifications | Important Assumptions
Overall Goal
Sustainable management of solid waste in the Pacific Region is enhanced. |  |  | 3R is practiced nation-wide | Monitoring reports of National Waste Management Strategy3)
Project Purpose |  |  |  |  | 1. Natural disaster would not drastically affect the collaboration among PICs and SPREP. 2. Political changes of PICs would not drastically affect the collaboration among PICs and SPREP.
Human and institutional capacity base for sustainable Solid Waste Management in the Pacific Region is strengthened through implementation of the Pacific Regional Solid Waste Management Strategy (2010-2015) (RS2010) |  |  | 1. 15 of experts (Trainers) in the SPREP inventory | SPREP (Regional inventory of skilled people)
|  |  | 2. Regional training program organized by Fiji is established. | Regional training program
# | Priorities under RS2010 | Outputs
1 | Sustainable Financing |  |  |  | 1. Political change in Fiji will not drastically affect the project implementation.
2-1 | 3Rs/4Rs | Output 1: National 3R strategy1) has been widely implemented in Fiji. | 1-1. 100% of councils2) have been implementing the 3R promotion in the Western Division. 1-2. Targeted components of 3R promotion for each council has been steadily progressed | 1-1 3R annual monitoring reports from councils and rural authorities 1-2 Same as above
2-2 | Waste Disposal
2-3 | Waste Collection
3 | Legislation
4 | Awareness/Communication/Education
5 | Capacity Building | Output 2: Fiji 3R model is disseminated to the Region/Country through training program. | 2-1 Training manuals/materials 2-2 # of trainig conducted and # of participants | 2-1 Developed manuals/materials 2-2 Participants lists
6 | Environmental Monitoring
7 | Policy,Planning, Performance
8 | Solid Waste Industry
* | Monitoring system of RS2010
| Activities |  | Inputs
|  | Please see PO for details. | Japanese Side | Fiji side | 1.Counterpart personnel keep working in the field of SWM. 2. Disasters, such as severe rain storm will not drastically affect the progress of project activities. 3. Necessary budget to carry out activities is allocated by the government.
|  |  | Dispatch of JICA experts | Assignment of National PD/PM and CPs
|  |  | Provision of equipment and materials Provision of Regional, sub-regional and in-country workshops / training | Local Costs Sharing Provision of necessary land/facility, work space
|  |  | Local cost support |  | Pre-condition
1): National 3R strategy is regarded as National 3R policy and National SWM strategy (2011 -1014)
2): 100% of councils means six (6) councils of the Western Division including LCC, NTC, STC, BTC, TTC, RTC
3): Fiji National Solid Waste Management Strategy 2011-2014 will be replaced with "National Waste Management Strategy" (a name that has been assumed temporarily)