Appendix 6 – Detailed list of contracts

| **Contract name** | **Contract amount and currency (taxes included)** | **Type of contract[[1]](#footnote-1)** | **Type of competition)[[2]](#footnote-2)** | **Procurement procedure[[3]](#footnote-3)** | **Selection method[[4]](#footnote-4)** | **Review by AFD[[5]](#footnote-5)** |  **Specific Procurement Notice Publication date** |  **Bid or Proposal Opening date** | **Contract signing date** | **Contract completion date** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| *SPREP Kiwa GESI strategy* |

|  |
| --- |
| *Projected: EUR 12 500* |

 | *C* | *IPC* | *REOI* | *QCBS* | PRIOR | *26/02/22* | *26/02/2022* | To take place in May 2022 | *June 2022* |
| *CReME TA support: Cook Islands* |

|  |  |  |
| --- | --- | --- |
| *Projected : /**Actual: EUR 8 850*

|  |
| --- |
|  |
|  |

 |

 | *C* | *IPC* | *RQ* | *QCBS* | PRIOR | *Not an open tender process* | *16/02/2022* | *24/03/2022* | *14 April 2022* |
| *CReME TA support: Tuvalu* | *Projected: /**Actual : EUR 8 477* | *IC* | *IPC* | *RQ* | *QCBS* | PRIOR | *Not an open tender process* | *17/02/2022* | *26/03/2022* | *14 April 2022* |
| *CReME TA support: Niue* | *Projected: /**Actual: EUR 8 185* | *C* | *IPC* | *RQ* | *QCBS* | PRIOR | *N/A* | *23/02/2022* | *23/03/2022* | *14 April 2022* |
| Training programme – NbS and EbA for climate change adaptation (Activity 1.1.1) |

|  |
| --- |
| *Projected**€ 72,500* |
| *Actual* |
| *Difference* |

 | *C* | *IPC* | *REOI* | *QCBS* | PRIOR | *November 2021* | *December 2021* | *January 2022* | *March 2023* |
| Support programme – Mainstreaming NbS into regional, national and local policies (Activity 1.1.2) |

|  |
| --- |
| *Projected**€ 60,000* |
| *Actual* |
| *Difference* |

 | *C* | *IPC* | *REOI* | *QCBS* | PRIOR | *October 2023* | *December 2023* | *January 2024* | *September 2024* |
| Communications (Activity 1.2) | *Projected**€ 10,500* | *C* | *IPC* | *REOI* | *QCSB* | PRIOR | *July 2022* | *August 2022* | *September 2022* | *March 2025* |
| Sustainability programme - sustainable finance mechanisms with countries involved in regional projects (Activity 3.1.2) |

|  |
| --- |
| *Projected**€ 38,000* |
| *Actual* |
| *Difference* |

 | *C* | *IPC* | *REOI* | *QCBS* | PRIOR | *January 2024* | *March 2024* | *April 2024* | *October 2024* |
| Development of a database on NbS for Climate Change adaptation in the Pacific (Activity 3.1.2) |

|  |
| --- |
| *Projected**€ 16,800* |
| *Actual* |
| *Difference* |

 | *C* | *IPC* | *REOI* | *QCBS* | PRIOR | *October 2022* | *November 2022* | *December 2022* | *April 2023* |
| Publication services | *Projected**TBD**Actual**Difference* | *IC* | *NPC* | *REOI* | *QCBS* | PRIOR | *January 2022* | *February 2022* | *March 2022* | *March 2025* |
| Translation services (EN/FR) |

|  |
| --- |
| *Projected**€ 55,000* |
| *Actual* |
| *Difference* |

 | *IC* | *IPC* | *REOI* | *QCBS* | PRIOR | *January 2022* | *March 2022* | *April-May 2022* | *October 2024* |
| Interpretation services (EN/FR, physical and online) |

|  |
| --- |
| *Projected**€ 26,000* |
| *Actual* |
| *Difference* |

 | *IC* | *IPC* | *REOI* | *QCBS* | PRIOR |  |  | *During meetings* |  |
| External Audits |

|  |
| --- |
| *Projected**€ 18,000* |
| *Actual* |
| *Difference* |

 | *IC* | *IPC* | *RQ* | *FBS* | / | *September 2022* | *October 2022* | *November 2022* | *March 2025* |

1. C for consulting services; IC for individual consultants; W for works; G for goods; P for Plants; NC for non-consulting services. [↑](#footnote-ref-1)
2. NPC: national procurement competition; IPC: international procurement competition. [↑](#footnote-ref-2)
3. For goods, works, plants and non-consulting services: PQL+IB: Prequalification and Invitation for Bids; IB: Invitation for Bids; RQ: Request for Quotations; DC: Direct Contracting.

For consulting services: REOI: Request for Expression of Interest; RQ: Request for Quotations; DC: Direct Contracting. [↑](#footnote-ref-3)
4. For consulting services: QCBS: Quality and Cost Based Selection; QBS: Quality Based Selection; FBS: Fixed Budget Based Selection; LCS: Least Cost Based Selection.

 For goods, works, plants and non-consulting services, the contract should be awarded to the qualified bidder whose bid is technically substantially compliant and is the lowest evaluated bid; other selection method shall require prior approval from AFD. [↑](#footnote-ref-4)
5. Decision to carry out Post reviews requires AFD’s prior approval. [↑](#footnote-ref-5)