## Ver.0
ANNEX III-2 : PO - Palau
Term: 2011 ～ 2015 (5years)
| Indicators for Project Purpose | 1. Recycling rate for beverage container is increased.
Outputs and Associated Activities |  | Indicators for Outputs | Person in-charge | Technical Assistance | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014 | [11 empty] | 2015
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
JCC/SC/Eva | JCC
Steering Committee
Evaluation Studies
OUTPUT 1: Beverage container deposit fee program (sustainable financing system) is enhanced. |  | 1-1 % of amount of containers redeemed out of imported beverage containers by the end of the Project.
1-1 | Implement the beverage container deposit fee program |  | Solid Waste Manager Office, BPW Solid Waste Management Office, Koror State Director of Tax Office, MOF
1-2 | Monitor the beverage container deposit fee program (monthly)
1-3 | Revise the beverage container deposit fee program reflecting the findings through monitoring | bar: 2011 9; 2012 3; 2012 8; 2013 8; 2014 8; 2015 8
OUTPUT 2: Awareness raising on 3R is enhanced. |  | 2-1 Manual/materials for awareness-raising is developed. 2-2 PEEC meetings are conducted on a monthly basis. | bar: 2011 1
2-1 | Facilitate the approval of the NSWMP (and obtain the approval) |  | Manager of SWMO, BPW | bar: 2011 1
2-2 | Prepare the action plan of awareness raising / environmental education on 3R for all states |  | SWM educator of SMWO, BPW | bar: 2011 3 to 2011 9
2-3 | Conduct the periodical meeting of PEEC (public education and enhancement committee) activities |  | SWM educator of SMWO, BPW | bar: 2011 4; 2011 6; 2011 9; 2011 12; 2012 3; 2012 6; 2012 9; 2012 12; 2013 3; 2013 6; 2013 9; 2013 12; 2014 3; 2014 6; 2014 9; 2014 12; 2015 3; 2015 6; 2015 9; 2015 12
2-4 | Conduct periodic workshops / campaign on 3R of SWM |  | SWM educator of SMWO, BPW | bar: 2011 4; 2011 9; 2012 4; 2012 8; 2013 4; 2013 8; 2014 4; 2014 8; 2015 4; 2015 8
2-5 | Prepare the plan to set up the segregation point in all states |  | Manager of SWMO, BPW | bar: 2011 4 to 2011 5; 2012 4 to 2012 5; 2013 4 to 2013 5; 2014 4 to 2014 5; 2015 4 to 2015 5
2-6 | Develop and revise the manual / materials on 3R reflecting the lessons learned. |  | SWM educator of SMWO, BPW | bar: 2013 1 to 2013 3; 2015 2 to 2015 4
OUTPUT 3: Final landfill site is improved. |  | 3-1 The closure plan for M-dock landfill is officially submitted to EQPB for approval. 3-2 EIA for the new landfill site is conducted. | bar: 2011 1
3-1 | Develop the plan of new dike for M-dock landfill |  | Manager of SWMO, BPW | bar: 2011 1 to 2011 3; 2011 9; 2012 9; 2013 9; 2014 9; 2015 9
3-2 | Construct the new dike for M-dock landfill | bar: 2011 5 to 2011 10
3-3 | Prepare a plan for safe closure of M-dock landfill | bar: 2013 9 to 2013 11
3-4 | Select the site and conduct the survey of a new national landfill | bar: 2012 2 to 2012 7
3-5 | Conduct the EIA for the new national landfill site | bar: 2012 8 to 2013 1
OUTPUT 4: Training program on 3R / recycling program is developed. |  | 4-1 Training manual / materials is developed.
4-1 | Develop the training program on 3R / recycling program to be used at the regional training/workshop |  | Manager of SWMO, BPW Solid Waste Management Office, Koror State | bar: 2013 10 to 2013 12
4-2 | Coduct the workshop to share the information on deposit fee program | bar: 2012 11
4-3 | Conduct the training for Micronesian area training /workshop (This includes in-country training conducted in other countries) | * This activity is also included in the Region-wide PO | bar: 2014 6; 2015 4
4-4 | Evaluate the training / revise the training program with feedbacks | bar: 2015 8

## Ver.0+Actual
ANNEX III-2 : PO - Palau
Term: 2011 ～ 2015 (5years)
Ver.0+ situation of April 2011
Outputs and Associated Activities |  | Indicators for Outputs | Person in-charge | Technical Assistance |  | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014 | [11 empty] | 2015
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
JCC/SC/Eva | JCC
Steering Committee
Evaluation Studies
OUTPUT 1: Beverage container deposit fee program (sustainable financing system) is enhanced.
1-1 | Implement the beverage container deposit fee program | 1-1 % of amount of containers redeemed out of imported beverage containers by the end of the Project. | Kalvin |  | Before
Revised
1-2 | Develop reports according to Recycling regulation |  | Kalvin |  | Before
Revised
1-3 | Revise the beverage container deposit fee program reflecting the findings through monitoring |  | Kalvin |  | Before
Revised | bar: 2011 9; 2012 3; 2012 8; 2013 8; 2014 8; 2015 8
OUTPUT 2: National Solid Waste Management Plan(NSWMP) is approved by the Government of Palau and revise the Action Plan for 2012-2016.
'2-1 | Facilitate the approval of the NSWMP (and obtain the approval) | 2-1 NSWMP is approved by the Government of Palau and Action Plan is revised. | Kalvin | bar: 2011 9; 2012 3; 2012 8; 2013 8; 2014 8; 2015 8
'2-2 | Revise the Action Plan of NSWMP |  | Kalvin | bar: 2011 9; 2012 3; 2012 8; 2013 8; 2014 8; 2015 8
OUTPUT 3: Awareness raising on 3R(including beverage Container Deposit Fee Program) is enhanced.
3-1 | Prepare the action plan of awareness raising / environmental education on 3R for all states | 3-1 Materials for awareness raising is developed. '3-2 PEEC meetings are conducted on a monthly basis, | MOn |  | Before
Revised | bar: 2011 5 to 2011 6
3-2 | Conduct the periodical meeting of PEEC (public education and enhancement committee) activities |  |  |  | Before
Revised | bar: 2011 5 to 2011 10; 2011 12; 2012 3; 2012 6; 2012 9; 2012 12; 2013 3; 2013 6; 2013 9; 2013 12; 2014 3; 2014 6; 2014 9; 2014 12; 2015 3; 2015 6; 2015 9; 2015 12
3-3 | Conduct periodic workshops / campaign on 3R of SWM |  |  |  | Before
Revised | bar: 2011 8 to 2011 10; 2012 4; 2012 8; 2013 4; 2013 8; 2014 4; 2014 8; 2015 4; 2015 8
3-4 | Develop and revise the manual / materials on 3R reflecting the lessons learned. |  |  |  | Before
Revised | bar: 2011 7 to 2011 9; 2013 1 to 2013 3; 2015 2 to 2015 4
OUTPUT 4: Final landfill site is improved.
4-1 | Develop the plan of new dike for M-dock landfill | 4-1 The closure plan for M-dock landfill is officially submitted to EQPB for approval. 4-2 EIA for the new landfill site is conducted. | Kalvin |  | Before | bar: 2011 9; 2012 9; 2013 9; 2014 9; 2015 9
Revised | bar: 2011 5 to 2011 10
4-2 | Construct the new dike for M-dock landfill |  |  |  | Before
Revised | bar: 2012 1 to 2013 12
4-3 | Prepare a plan for safe closure of M-dock landfill |  |  |  | Before
Revised | bar: 2013 9 to 2013 11
4-4 | Select the site and conduct the survey of a new national landfill |  |  |  | Before
Revised | bar: 2012 2 to 2012 7
4-5 | Conduct the EIA for the new national landfill site |  |  |  | Before
Revised | bar: 2012 8 to 2013 1
OUTPUT 5: Training program on 3R / recycling program is developed.
5-1 | Develop the training program on 3R / recycling program to be used at the regional training/workshop | 5-1 Training manual / materials is developed. | Mon |  | Before
Revised | bar: 2013 10 to 2013 12
5-3 | Conduct the training for Micronesian area training /workshop (This includes in-country training conducted in other countries) |  |  |  | Before
Revised | bar: 2014 6; 2015 4
5-4 | Evaluate the training / revise the training program with feedbacks |  |  |  | Before
Revised | bar: 2015 8

## Ver.3
ANNEX II : PO - Palau | [57 empty] | Jan. 2014
Term: 2011 ～ 2015 (5years) | [57 empty] | Version .3
Outputs and Associated Activities |  | Indicators for Outputs | Person in-charge | Technical advice | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014 | [11 empty] | 2015
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
JCC/SC/Eva | JCC
Steering Committee
Evaluation Studies
OUTPUT 1: Capacity to manage the beverage container deposit fee program (sustainable financing system) is enhanced.
1-1 | Implement the beverage container deposit fee program | 1-1: % of amount of containers redeemed out of imported beverage containers by the end of the Project. 1-2: The financial balance between income and expenditured of BCDFP is well maintaned. | Calvin
1-2 | Conduct regular meeting and revise the program if necessary. |  | Calvin | bar: 2013 4; 2013 11; 2014 4; 2014 11; 2015 4; 2015 11
OUTPUT 2: National Solid Waste Management Plan is finalized and Action Plan is revised.
'2-1 | Facilitate the approval of the NSWMP (and obtain the approval) | 2-1: NSWMP is finalized. 2-2: Action Plan is revised. | Calvin | bar: 2011 5 to 2011 7
'2-2 | Revise the Action Plan of NSWMP if necessary |  | Calvin | SPREP | bar: 2012 6 to 2012 7; 2013 3; 2014 3; 2015 3
OUTPUT 3: Capacity to conduct Awareness raising on 3R (targeting MPIIC and Eathday) is enhanced.
3-1 | Prepare the action plan of awareness raising / environmental education on 3R and finalize it | 3-1: Materials are delivered to 50% of schools in the Earth day activity. 3-2: # of installed recycling bins at MPIIC. | Mengkur | bar: 2013 8 to 2014 1
3-2 | Implement the Action Plan. |  | Mengkur | bar: 2014 1 to 2015 12
3-3 | Develop and revise the tools/materials on 3R reflecting the lessons learned. |  | Mengkur | bar: 2014 1 to 2014 4
OUTPUT 4: Capacity to manage the final landfill site is enhanced.
4-1 | Develop the plan of new dike for M-dock landfill | 4-1: A period of operation for M-Dock is extended for 3 years. 4-2: The existing closure plan for M-dock landfill is revised. 4-3: Conceptional Plan of the waste disposal is developed. | Calvin | bar: 2011 5 to 2011 10
4-2 | Construct the new dike for M-dock landfill |  | Calvin | bar: 2012 5 to 2013 2
4-3 | Conduct a survey to estimate the remaining capacity of M-Dock landfill |  | Calvin | bar: 2014 5 to 2014 6
4-4 | Prepare a plan for safe closure of M-dock landfill |  | Calvin | JICA | bar: 2014 9 to 2014 11
4-5 | Select the site of a new national landfill |  | Calvin | bar: 2013 6 to 2014 7
4-6 | Prepare EIA for the new national landfill. |  | Calvin | bar: 2014 5 to 2014 12
4-7 | Develop a conceptional plan of the waste disposal. |  | Calvin | JICA | bar: 2014 5 to 2015 3
OUTPUT 5: Training program on 3R / SWM is developed.
5-1 | Develop the training program on 3R /SWM to be used at the regional training/workshop | 5-1 Training manual / materials is developed. 5-2: # of training conducted and # of participants | John | JICA | bar: 2013 2 to 2013 6; 2014 11 to 2015 6
5-2 | Conduct the training for Micronesian area training /workshop (This includes in-country training conducted in other countries) |  | John | JICA | bar: 2013 11; 2015 7
5-3 | Evaluate the training / revise the training program with feedbacks |  | John | JICA | bar: 2013 12; 2015 7 to 2015 8

## Ver.3 +actual
ANNEX II : PO - Palau | [57 empty] | Mar. 2015
Term: 2011 ～ 2015 (5years) | [57 empty] | Version .3+Actual
Outputs and Associated Activities |  | Indicators for Outputs | Person in-charge | Plan | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014 | [11 empty] | 2015
|  |  |  | Actual | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
JCC/SC/Eva | JCC
Steering Committee
Evaluation Studies
OUTPUT 1: Capacity to manage the beverage container deposit fee program (sustainable financing system) is enhanced.
1-1 | Implement the beverage container deposit fee program | 1-1: % of amount of containers redeemed out of imported beverage containers by the end of the Project. 1-2: The financial balance between income and expenditured of BCDFP is well maintaned. | Calvin | Plan
Actual
1-2 | Conduct regular meeting and revise the program if necessary. |  | Calvin | Plan
Actual
OUTPUT 2: National Solid Waste Management Plan is finalized and Action Plan is revised.
'2-1 | Facilitate the approval of the NSWMP (and obtain the approval) | 2-1: NSWMP is approved by the Government of Palau and Action Plan is revised. | Calvin | Plan
Actual
'2-2 | Revise the Action Plan of NSWMP if necessary |  | Calvin | Plan
Actual
OUTPUT 3: Capacity to conduct Awareness raising on 3R (targeting MPIIC and Eathday) is enhanced.
3-1 | Prepare the action plan of awareness raising / environmental education on 3R and finalize it | 3-1: Materials are deliverd to 50% of schools in the Earth day activity. 3-2: # of installed recycling bins at MPIIC. | Mengkur | Plan
Actual
3-2 | Implement the Action Plan. |  | Mengkur | Plan
Actual
3-3 | Develop and revise the tools/materials on 3R reflecting the lessons learned. |  | Mengkur | Plan
Actual
OUTPUT 4: Capacity to manage the final landfill site is enhanced.
4-1 | Develop the plan of new dike for M-dock landfill | 4-1: The closure plan for M-dock landfill is officially submitted to EQPB for approval. 4-2: EIA for the new landfill site is conducted. 4-3: Selection of site for new landfill is approved by landowner. | Calvin | Plan
Actual
4-2 | Construct the new dike for M-dock landfill |  | Calvin | Plan
Actual
4-3 | Conduct a survey to estimate the remaining capacity of M-Dock landfill |  | Calvin | Plan
Actual
4-4 | Prepare a plan for safe closure of M-dock landfill |  | Calvin | Plan
Actual
4-5 | Select the site of a new national landfill |  | Calvin | Plan
Actual
4-6 | Prepare EIA for the new national landfill. |  | Calvin | Plan
Actual
4-7 | Develop a conceptional plan of the waste disposal. |  | Calvin | Plan
Actual
OUTPUT 5: Training program on 3R / SWM is developed.
5-1 | Develop the training program on 3R / recycling program to be used at the regional training/workshop | 5-1 Training manual / materials is developed. 5-2: # of training conducted and # of participants | John | Plan
Actual
5-2 | Conduct the training for Micronesian area training /workshop (This includes in-country training conducted in other countries) |  | John | Plan
Actual
5-3 | Evaluate the training / revise the training program with feedbacks |  | John | Plan
Actual
Progress in 2014

## Ver.4
ANNEX II : PO - Palau | [57 empty] | Mar. 2015
Term: 2011 ～ 2015 (5years) | [57 empty] | Version .4
Outputs and Associated Activities |  | Indicators for Outputs | Person in-charge | Technical advice | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014 | [11 empty] | 2015
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
JCC/SC/Eva | JCC
Steering Committee
Evaluation Studies
OUTPUT 1: Capacity to manage the beverage container deposit fee program (sustainable financing system) is enhanced.
1-1 | Implement the beverage container deposit fee program | 1-1: % of amount of containers redeemed out of imported beverage containers by the end of the Project. 1-2: Amount of shipped off containers. | Calvin
1-2 | Conduct regular meeting and revise the program if necessary. |  | Calvin | bar: 2013 4; 2013 11; 2014 4; 2014 11; 2015 4; 2015 11
OUTPUT 2: National Solid Waste Management Plan is finalized and Action Plan is revised.
'2-1 | Facilitate the approval of the NSWMP (and obtain the approval) | 2-1: NSWMP is finalized. 2-2: Action Plan is revised. | Calvin | bar: 2011 5 to 2011 7
'2-2 | Revise the Action Plan of NSWMP if necessary |  | Calvin | SPREP | bar: 2012 6 to 2012 7; 2013 3; 2014 3; 2015 5
OUTPUT 3: Capacity to conduct Awareness raising on 3R (targeting MPIIC and Eathday) is enhanced.
3-1 | Prepare the action plan of awareness raising / environmental education on 3R and finalize it | 3-1: Materials are delivered to 50% of schools in the Earth day activity. 3-2: # of school presentations/ visits & conducted workshops | Mengkur | bar: 2013 8 to 2014 1
3-2 | Implement the Action Plan. |  | Mengkur | bar: 2014 1 to 2015 12
3-3 | Develop and revise the tools/materials on 3R reflecting the lessons learned. |  | Mengkur | bar: 2014 1 to 2014 4; 2015 4 to 2015 5
OUTPUT 4: Capacity to manage the final landfill site is enhanced.
4-1 | Develop the plan of new dike for M-dock landfill | 4-1: A period of operation for M-Dock is extended for 3 years. 4-2: The existing closure plan for M-dock landfill is revised. 4-3: Conceptional Plan of the waste disposal is developed. | Calvin | bar: 2011 5 to 2011 10
4-2 | Construct the new dike for M-dock landfill |  | Calvin | bar: 2012 5 to 2013 2
4-3 | Conduct a survey to estimate the remaining capacity of M-Dock landfill |  | Calvin | bar: 2014 5 to 2014 6
4-4 | Prepare a plan for safe closure of M-dock landfill |  | Calvin | JICA | bar: 2014 9 to 2014 11; 2015 8
4-5 | Select the site of a new national landfill |  | Calvin | bar: 2013 6 to 2014 7
4-6 | Prepare EIA for the new national landfill. |  | Calvin | bar: 2015 4
4-7 | Develop a conceptional plan of the waste disposal. |  | Calvin | JICA | bar: 2015 4 to 2015 5
OUTPUT 5: Training program on 3R / SWM is developed.
5-1 | Develop the training program on 3R /SWM to be used at the regional training/workshop | 5-1 Training manual / materials is developed. 5-2: # of training conducted and # of participants | John | JICA | bar: 2013 2 to 2013 6; 2014 11 to 2015 6
5-2 | Conduct the training for Micronesian area training /workshop (This includes in-country training conducted in other countries) |  | John | JICA | bar: 2013 11; 2015 8
5-3 | Evaluate the training / revise the training program with feedbacks |  | John | JICA | bar: 2013 12; 2015 8